## Sheet1
Task/Management | Human Resources | Procurement | Communication | Risk
1. Initiating
1.1 Media proposal | P
1.2 Estimate cost/budget |  | P
1.3 Collect purchase requests
1.4 Sponsor/supplier search |  |  | P
1.5 Analyse potential risks |  |  |  | P
2. Planning
2.1 Hire employees | P
2.2 Organize list of required assets |  | P
2.3 Contacting sponsors |  | P | P
2.4 Establishing internal communication |  |  | P
2.5 Prepare T&C for sponsors/suppliers |  |  | P
2.6 Insurance acquirement |  |  |  | P
3. Executing
3.1 Organize employees | P
3.2 Compile Work Breakdown Structure | P
3.3 Negotiate with sponsors/suppliers |  | P
3.4 Create sponsors/ suppliers connections |  |  | P
3.5 Allocate insurance claims |  |  |  | P
4. Monitoring & Controlling
4.1 Weekly updates on department progress | P
4.2 Observe department managers and staffs | P
4.3 Inform supplies' progress |  | P
4.4 Monitor departments' progress |  |  | P
4.5 Oversee risk containment's progress |  |  |  | P
5. Closing
5.1 Document report on departments' progress | P
5.2 Document report on obtained supplies/services |  | P
5.3 Document report on messeges/mails |  |  | P
5.4 Document report on losses |  |  |  | P