## Sheet1
Task/Management | Human Resources | Procurement | Communication | Risk
1. Initiating
1.1 Develop Project Charter | P
1.2 Collect Purchase Requests |  | P
1.3 Identify Stakeholders |  |  | P
1.4 Sponsor/Supplier Search |  |  | P
1.5 Analyse Potential Risks |  |  |  | P
2. Planning
2.1 Plan Human Resource Management | P
2.2 Organize List of Required Assets |  | P
2.3 Plan Communications Management
2.4 Contacting Sponsors |  |  | P
2.5 Plan Risk Management |  |  |  | P
2.6 Identify Risks |  |  |  | P
2.7 Perform Risk Analysis |  |  |  | P
2.8 Plan Risk Responses |  |  |  | P
3. Executing
3.1 Acquire Project Team | P
3.2 Develop Project Team | P
3.3 Manage Project Team | P
3.4 Contacting & Negotiate with Sponsors/Suppliers |  | P
3.5 Conduct Procurement |  | P
3.6 Manage Communications |  |  | P
3.7 Manage Stakeholder Expectations |  |  | P
3.8 Execute Risk Responses |  |  |  | P
4. Monitoring & Controlling
4.1 Monitor Project Team Progress | P
4.2 Control Procurement |  | P
4.3 Control Communications |  |  | P
4.4 Monitor and Control Risks |  |  |  | P
5. Closing
5.1 Close Project | P
5.2 Close Procurements |  | P
5.4 Document Procurement Report |  | P
5.6 Document Report on Losses |  |  |  | P

## Sheet2
Resource Name | Amount | Std. Rate | Working Month/Week/Day/Hour | Calculation | Cost
Project Manager | 1 | $3000/mon | 4 Months | 7000 x 4 | 28000
Software Engineer | 3 | $2200/mon | 4 Months | 2200 x 4 x 3 | 26400
UI Designer | 1 | $1800/mon | 4 Months | 1800 x 4 | 7200
Software Tester | 1 | $1000/mon | 1 Month | 1000 | 1000
Quality Control | 1 | $1700/day | 4 Months | 1700 x 4 | 6800
IT Security | 1 | $1800/mon | 4 Months | 1800 x 4 | 7200
Technical Assistant | 1 | $1800/mon | 4 Months | 1800 x 4 | 7200
|  |  |  | Total: | 83800

## Sheet3
Task/Management | Cost
1 Initiating | 2400
1.1 Identify Stakeholders | 100
1.2 System Proposal | 300
1.3 Feasibility Studies | 800
1.3.1 Technical Feasibility Study | 200
1.3.2 Schedule Feasibility Study | 200
1.3.3 Financial Feasibility Study | 200
1.3.4 Resource Feasibility Study | 200
1.4 Develop Project Charter | 1200
1.4.1 Determine Project Aim & Objectives | 200
1.4.2 Determine Project Scope | 200
1.4.3 Determine Project Budget | 200
1.4.4 Determine Project Roles | 200
1.4.5 Determine Project Risks | 200
1.4.6 Determine Project Milestones | 200
2 Planning | 2700
2.1 Develop Project Plan | 500
2.1.1 Identify Phases & Activities | 250
2.1.2 Create Project Planning Schedule | 250
2.2 Develop Resource Plan | 400
2.2.1 Identify Types of Tasks | 100
2.2.2 Identify Number of Staff | 100
2.2.3 Identify Needed Equipment | 100
2.2.4 Identify Equipment Types & Quantity | 100
2.3 Develop Financial Plan | 300
2.3.1 Identify Labour Costs | 100
2.3.2 Identify Equipment Costs | 100
2.3.3 Identify Miscellaneous Costs | 100
2.4 Develop Quality Plan | 400
2.4.1 Identify Customers Requirements | 100
2.4.2 List Project Deliverables | 100
2.4.3 Define Quality Standards for Deliverables | 100
2.4.4 Customer Approval for Set Targets | 100
2.5 Develop Risk Plan | 200
2.5.1 Identify Project Risks | 100
2.5.2 Categorize & Prioritize Risks | 100
2.6 Develop Communication Plan | 400
2.6.1 List Communications Stakeholders | 200
2.6.2 Define Communication Needs | 200
2.7 Develop Procurement Plan | 500
2.7.1 Determine Procurement Requirements | 100
2.7.2 Identify Needed Procurement | 100
2.7.3 Create Financial Justification | 300
3 Execution | 119000
3.1 Requirement Gathering | 10000
3.1.1 Client Interview | 1000
3.1.2 Construct Use Case | 1000
3.1.3 Prototyping | 8000
3.2 Procurement | 50000
3.2.1 Compare Supplier Prices | 0
3.2.2 Negotiate Prices | 0
3.2.3 Obtain Hardware | 25000
3.2.4 Obtain Software | 25000
3.3 Staff Management | 4000
3.3.1 Hire Staff | 3000
3.3.2 Allocate Human Resources | 250
3.3.3 Labour Tracking | 250
3.3.4 Training Tracking | 250
3.3.5 Time Tracking | 250
3.4 Development | 50000
3.4.1 Functional Development | 10000
3.4.2 Technical Development | 20000
3.4.3 Application Development | 20000
3.5 Testing | 5000
3.5.1 Application Development Centre Testing | 1000
3.5.2 IT Regression Testing | 2000
3.4.3 User Acceptance Testing | 2000
3.6 System Setup | 0
3.6.1 Hardware Installation | 0
3.6.2 System Installation | 0
4 Monitoring & Controlling | 500
4.1 HR Management | 200
4.1.1 Control Man Days | 100
4.1.2 Monitor Staff Progress | 100
4.2 Procurement Management | 200
4.2.1 Quantity Control | 100
4.2.2 Quality Control | 100
4.3 Quality Deliverables | 100
4.3.1 Testing Reports | 100
5 Closing | 800
5.1 Documentation | 400
5.1.1 Procurement Report | 100
5.1.2 Financial Report | 100
5.1.3 Project Documentation | 100
5.1.4 Stakeholders Approval & Signature | 100
5.2 Formal Acceptance & Information | 400
5.2.1 Inform Stakeholders | 100
5.2.2 Stakeholders Approval & Signature | 100
5.2.3 End Staff Employment | 100
5.2.4 End Supplier Contract | 100
TOTAL: | 125400