## Slide 1
LECTURE 05
Project Scope Management

## Slide 2: Learning Objectives
Understand the importance of good project scope management
Describe the process of planning scope management
Discuss methods for collecting and documenting requirements to meet stakeholder needs and expectations
Explain the scope definition process and describe the contents of a project scope statement
Discuss the process for creating a work breakdown structure using the analogy, top-down, bottom-up, and mind-mapping approaches

## Slide 3: Learning Objectives
Explain the importance of validating scope and how it relates to defining and controlling scope
Understand the importance of controlling scope and approaches for preventing scope-related problems on information technology (IT) projects
Describe how software can assist in project scope management

## Slide 4: What is Project Scope Management?
Scope refers to all the work involved in creating the products of the project and the processes used to create them
A deliverable is a product produced as part of a project, such as hardware or software, planning documents, or meeting minutes
Project scope management includes the processes involved in defining and controlling what is or is not included in a project

## Slide 5: Project Scope Management Processes
Planning scope: determining how the project’s scope
and requirements will be managed
Collecting requirements: defining and documenting the features and functions of the products produced during the project as well as the processes used for creating them
Defining scope: reviewing the project charter, requirements documents, and organizational process assets to create a scope statement
Creating the WBS: subdividing the major project deliverables into smaller, more manageable components
Validating scope: formalizing acceptance of the project deliverables
Controlling scope: controlling changes to project scope throughout the life of the project

## Slide 6: Figure 5-1. Project Scope Management Summary

## Slide 7: Planning Scope Management
The project team uses expert judgment and meetings to develop two important outputs: the scope management plan and the requirements management plan
The scope management plan is a subsidiary part of the project management plan

## Slide 8: Scope Management Plan Contents
How to prepare a detailed project scope statement
How to create a WBS
How to maintain and approve the WBS
How to obtain formal acceptance of the completed project deliverables
How to control requests for changes to the project scope

## Slide 9: Requirements Management Plan
The PMBOK® Guide, Fifth Edition, describes requirements as “conditions or capabilities that must be met by the project or present in the product, service, or result to satisfy an agreement or other formally imposed specification”
The requirements management plan documents how project requirements will be analyzed, documented, and managed

## Slide 10: What Went Right?
Projected number of jobs for business analysts expected to increase 19 percent by 2022
Only 49 percent of survey respondents had the resources in place to do requirements management properly and 53 percent failed to use a formal process to validate requirements
There are several certifications available for business analysis to help meet this need

## Slide 11: Collecting Requirement
For some IT projects, it is helpful to divide requirements development into categories called elicitation, analysis, specification, and validation
It is important to use an iterative approach to defining requirements since they are often unclear early in a project

## Slide 12: Figure 5-2. Relative Cost to Correct a Software Requirement Defect

## Slide 13: Methods for Collecting Requirements
Interviewing
Focus groups and facilitated workshops
Using group creativity and decision-making techniques
Questionnaires and surveys
Observation
Prototyping
Benchmarking, or generating ideas by comparing specific project practices or product characteristics to those of other projects or products inside or outside the performing organization, can also be used to collect requirements

## Slide 14: Statistics on Requirements for Software Projects (2011 Survey)
88% of the software projects involved enhancing existing products instead of creating new ones
86% of respondents said that customer satisfaction was the most important metric for measuring the success of development projects
83% of software development teams still use Microsoft Office applications such as Word and Excel as their main tools to communicate requirements

## Slide 15: Requirements Traceability Matrix
A requirements traceability matrix (RTM) is a table that lists requirements, various attributes of each requirement, and the status of the requirements to ensure that all requirements are addressed
Table 5-1. Sample entry in an RTM

## Slide 16: Defining Scope
Project scope statements should include at least a product scope description, product user acceptance criteria, and detailed information on all project deliverables.
Include other scope-related information, such as the project boundaries, constraints, and assumptions with reference to supporting documents, such as product specifications
As time progresses, the scope of a project should become more clear and specific

## Slide 17: Table 5-2. Sample Project Charter (partial)

## Slide 18: Table 5-3: Further Defining Project Scope

## Slide 19: Creating the Work Breakdown Structure (WBS)
A WBS is a deliverable-oriented grouping of the work involved in a project that defines the total scope of the project
WBS is a foundation document that provides the basis for planning and managing project schedules, costs, resources, and changes
Decomposition is subdividing project deliverables into smaller pieces
A work package is a task at the lowest level of the WBS
The scope baseline includes the approved project scope statement and its associated WBS and WBS dictionary

## Slide 20: Figure 5-3. Sample Intranet WBS Organized by Product

## Slide 21: Figure 5-4. Sample Intranet WBS Organized by Phase

## Slide 22: Figure 5-5. Intranet WBS and Gantt Chart in Microsoft Project

## Slide 23: Figure 5-6. Intranet Gantt Chart Organized by Project Management Process Groups

## Slide 24: Table 5-4: Executing Tasks for JWD Consulting’s WBS

## Slide 25: Approaches to Developing WBSs
Using guidelines: Some organizations, like the DOD, provide guidelines for preparing WBSs
The analogy approach: Review WBSs of similar projects and tailor to your project
The top-down approach: Start with the largest items of the project and break them down
The bottom-up approach: Start with the specific tasks and roll them up
Mind-mapping approach: Mind mapping is a technique that uses branches radiating out from a core idea to structure thoughts and ideas

## Slide 26: Figure 5-7. Sample Mind-Mapping Approach for Creating a WBS

## Slide 27: Figure 5-8. Gantt Charts With WBS Generated From a Mind Map

## Slide 28: The WBS Dictionary and Scope Baseline
Many WBS tasks are vague and must be explained more so people know what to do and can estimate how long it will take and what it will cost to do the work
A WBS dictionary is a document that describes detailed information about each WBS item

## Slide 29: Table 5-5. Sample WBS Dictionary Entry

## Slide 30: Validating Scope
It is very difficult to create a good scope statement and WBS for a project
It is even more difficult to verify project scope and minimize scope changes
Scope validation involves formal acceptance of the completed project deliverables
Acceptance is often achieved by a customer inspection and then sign-off on key deliverables

## Slide 31: Controlling Scope
Scope control involves controlling changes to the project scope
Goals of scope control are to
  influence the factors that cause scope changes
  assure changes are processed according to procedures developed as part of integrated change control, and
  manage changes when they occur
Variance is the difference between planned and actual performance

## Slide 32: Using Software to Assist in Project Scope Management
Word-processing software helps create several scope-related documents
Spreadsheets help to perform financial calculations, weighed scoring models, and develop charts and graphs
Communication software like e-mail and the Web help clarify and communicate scope information
Project management software helps in creating a WBS, the basis for tasks on a Gantt chart
Specialized software is available to assist in project scope management

## Slide 33: Chapter Summary
Project scope management includes the processes required to ensure that the project addresses all the work required, and only the work required, to complete the project successfully
Main processes include
  Define scope management
  Collect requirements
  Define scope
  Create WBS
  Validate scope
  Control scope

## Slide 34: Questions & answers