## Slide 1
LECTURE 08
Project Human Resource Management

## Slide 2: Learning Objectives
Explain the importance of good human resource management on projects, including the current state of the global IT workforce and future implications for it
Define project human resource management and understand its processes
Summarize key concepts for managing people by understanding theories of motivation, influence, and power; how people and teams can become more effective; emotional intelligence; and leadership

## Slide 3: Learning Objectives
Discuss human resource management planning and be able to create a human resource plan, project organizational chart, responsibility assignment matrix, and resource histogram
Understand important issues involved in project staff acquisition and explain the concepts of resource assignments, resource loading, and resource leveling
Assist in team development with training, team-building activities, and reward systems
Explain and apply several tools and techniques to help manage a project team and summarize general advice on managing teams
Describe how project management software can assist in project human resource management

## Slide 4: The Importance of Human Resource Management
Many corporate executives have said, “People are our most important asset”
People determine the success and failure of organizations and projects

## Slide 5: What is Project Human Resource Management?
Making the most effective use of the people involved with a project
Processes include
  Planning human resource management: identifying and documenting project roles, responsibilities, and reporting relationships
  Acquiring the project team: getting the needed personnel assigned to and working on the project
  Developing the project team: building individual and group skills to enhance project performance
  Managing the project team: tracking team member performance, motivating team members, providing timely feedback, resolving issues and conflicts, and coordinating changes to help enhance project performance

## Slide 6: Figure 9-1. Project Human Resource Management Summary

## Slide 7: Keys to Managing People
Psychologists and management theorists have devoted much research and thought to the field of managing people at work
Important areas related to project management include
  motivation theories
  influence and power
  Effectiveness
  Emotional intelligence
  Leadership

## Slide 8: Intrinsic and Extrinsic Motivation
Intrinsic motivation causes people to participate in an activity for their own enjoyment
Extrinsic motivation causes people to do something for a reward or to avoid a penalty
For example, some children take piano lessons for intrinsic motivation (they enjoy it) while others take them for extrinsic motivation (to get a reward or avoid punishment)

## Slide 9: Maslow’s Hierarchy of Needs
Abraham Maslow argued that humans possess unique qualities that enable them to make independent choices, thus giving them control of their destiny
Maslow developed a hierarchy of needs which states that people’s behaviors are guided or motivated by a sequence of needs

## Slide 10: Figure 9-2. Maslow’s Hierarchy of Needs

## Slide 11: Herzberg’s Motivational and Hygiene Factors
Frederick Herzberg wrote several famous books and articles about worker motivation. He distinguished between
  motivational factors: achievement, recognition, the work itself, responsibility, advancement, and growth, which produce job satisfaction
  hygiene factors: cause dissatisfaction if not present, but do not motivate workers to do more. Examples include larger salaries, more supervision, and a more attractive work environment

## Slide 12: Table 9-1: Examples of Herzberg’s Hygiene Factors & Motivators

## Slide 13: Media Snapshot
RSA Animate used its popular whiteboard drawing technique to summarize key points from Pink’s book in a YouTube video called “Drive: The surprising truth about what motivates us”
Pink suggests that managers focus on the following three motivators:
  Autonomy
  Mastery
  Purpose

## Slide 14: McClelland’s Acquired-Needs Theory
Specific needs are acquired or learned over time and shaped by life experiences, including:
  Achievement (nAch): Achievers like challenging projects with achievable goals and lots of feedback
  Affiliation (nAff): People with high nAff desire harmonious relationships and need to feel accepted by others, so managers should try to create a cooperative work environment for them
  Power: (nPow): People with a need for power desire either personal power (not good) or institutional power (good for the organization). Provide institutional power seekers with management opportunities

## Slide 15: McGregor’s Theory X and Y
Douglas McGregor popularized the human relations approach to management in the 1960s
Theory X: assumes workers dislike and avoid work, so managers must use coercion, threats and various control schemes to get workers to meet objectives
Theory Y: assumes individuals consider work as natural as play or rest and enjoy the satisfaction of esteem and self-actualization needs
Theory Z: introduced in 1981 by William Ouchi and is based on the Japanese approach to motivating workers, emphasizing trust, quality, collective decision making, and cultural values

## Slide 16: Thamhain and Wilemon’s Ways to Have Influence on Projects
1. Authority: the legitimate hierarchical right to issue orders
2. Assignment: the project manager's perceived ability to influence a worker's later work assignments
3. Budget: the project manager's perceived ability to authorize others' use of discretionary funds
4. Promotion: the ability to improve a worker's position
5. Money: the ability to increase a worker's pay and benefits

## Slide 17: Thamhain and Wilemon’s Ways to Have Influence on Projects
6. Penalty: the project manager's ability to cause punishment
7. Work challenge: the ability to assign work that capitalizes on a worker's enjoyment of doing a particular task
8. Expertise: the project manager's perceived special knowledge that others deem important
9. Friendship: the ability to establish friendly personal relationships between the project manager and others

## Slide 18: Ways to Influence that Help and Hurt Projects
Projects are more likely to succeed when project managers influence with
  expertise
  work challenge
Projects are more likely to fail when project managers rely too heavily on
  authority
  money
  penalty

## Slide 19: Power
Power is the potential ability to influence behavior to get people to do things they would not otherwise do
Types of power include
  Coercive
  Legitimate
  Expert
  Reward
  Referent

## Slide 20: Covey and Improving Effectiveness
Project managers can apply Covey’s 7 habits to improve effectiveness on projects
  Be proactive
  Begin with the end in mind
  Put first things first
  Think win/win
  Seek first to understand, then to be understood
  Synergize
  Sharpen the saw

## Slide 21: Empathic Listening and Rapport
Good project managers are empathic listeners - they listen with the intent to understand
Before you can communicate with others, you have to have rapport – a relation of harmony, conformity, accord, or affinity
Mirroring is the matching of certain behaviors of the other person, a technique to help establish rapport
IT professionals need to develop empathic listening and other people skills to improve relationships with users and other stakeholders

## Slide 22: Emotional Intelligence
Howard Gardner’s book Frames of Mind: The Theory of Multiple Intelligences introduced the concept of using more than one way to think of and measure human intelligence
Emotional intelligence (EI) is knowing and managing one’s own emotions and understanding the emotions of others for improved performance
71 percent of U.S. hiring managers say they value EI more than IQ

## Slide 23: Leadership
There is no one best way to be a leader
Most experts agree that the best leaders are able to adapt their style to needs of the situation
Daniel Goleman, author of Emotional Intelligence and Primal Leadership, describes six leadership styles:
  Visionary
  Coaching
  Affiliative
  Democratic
  Pacesetting
  Commanding

## Slide 24: Developing the Human Resource Plan
Involves identifying and documenting project roles, responsibilities, and reporting relationships
Contents include
  project organizational charts
  staffing management plan
  responsibility assignment matrixes
  resource histograms

## Slide 25: Figure 9-3. Organizational Chart for a Large IT Project

## Slide 26: Figure 9-4. Work Definition and Assignment Process

## Slide 27: Responsibility Assignment Matrices
A responsibility assignment matrix (RAM) is a matrix that maps the work of the project as described in the WBS to the people responsible for performing the work as described in the OBS
Can be created in different ways to meet unique project needs

## Slide 28: Figure 9-5. Sample Responsibility Assignment Matrix (RAM)

## Slide 29: Table 9-2. Sample RACI Chart
R = responsibility
A = accountability, only one A per task
C = consultation
I = informed
Note that some people reverse the definitions of responsible and accountable.

## Slide 30: Staffing Management Plans and Resource Histograms
A staffing management plan describes when and how people will be added to and taken off the project team
A resource histogram is a column chart that shows the number of resources assigned to a project over time

## Slide 31: Figure 9-6. Sample Resource Histogram

## Slide 32: Acquiring the Project Team
Acquiring qualified people for teams is crucial
The project manager who is the smartest person on the team has done a poor job of recruiting!
It’s important to assign the appropriate type and number of people to work on projects at the appropriate times

## Slide 33: Resource Assignment
Staffing plans and good hiring procedures are important, as are incentives for recruiting and retention
  Some companies give their employees one dollar for every hour a new person they helped hire works
  Some organizations allow people to work from home as an incentive
Enrollment in U.S. computer science and engineering programs has dropped almost in half since 2000, and one-third of U.S. workers were over the age of 50 by 2010
CIO’s researchers suggest that organizations rethink hiring practices and incentives to hire and retain IT talent

## Slide 34: Resource Loading
Resource loading refers to the amount of individual resources an existing schedule requires during specific time periods
Helps project managers develop a general understanding of the demands a project will make on the organization’s resources and individual people’s schedules
Overallocation means more resources than are available are assigned to perform work at a given time

## Slide 35: Figure 9-7. Sample Histogram Showing an Overallocated Individual

## Slide 36: Resource Leveling
Resource leveling is a technique for resolving resource conflicts by delaying tasks
The main purpose of resource leveling is to create a smoother distribution of resource usage and reduce overallocation

## Slide 37: Figure 9-8. Resource Leveling Example

## Slide 38: Developing the Project Team
The main goal of team development is to help people work together more effectively to improve project performance
It takes teamwork to successfully complete most projects

## Slide 39: Tuckman Model of Team Development
Forming
Storming
Norming
Performing
Adjourning

## Slide 40: Training
Training can help people understand themselves, each other, and how to work better in teams
Team building activities include
  physical challenges
  psychological preference indicator tools

## Slide 41: Meyers-Briggs Type Indicator (MBTI)
MBTI is a popular tool for determining personality preferences and helping teammates understand each other
Four dimensions include:
  Extrovert/Introvert (E/I)
  Sensation/Intuition (S/N)
  Thinking/Feeling (T/F)
  Judgment/Perception (J/P)
NTs or rationals are attracted to technology fields
IT people vary most from the general population in not being extroverted or sensing

## Slide 42: Social Styles Profile
People are perceived as behaving primarily in one of four zones, based on their assertiveness and responsiveness:
  Drivers
  Expressives
  Analyticals
  Amiables
People on opposite corners (drivers and amiables, analyticals and expressives) may have difficulties getting along

## Slide 43: Figure 9-9. Social Styles

## Slide 44: Reward and Recognition Systems
Team-based reward and recognition systems can promote teamwork
Focus on rewarding teams for achieving specific goals
Allow time for team members to mentor and help each other to meet project goals and develop human resources

## Slide 45: Managing the Project Team
Project managers must lead their teams in performing various project activities
After assessing team performance and related information, the project manager must decide
  if changes should be requested to the project
  if corrective or preventive actions should be recommended
  if updates are needed to the project management plan or organizational process assets.

## Slide 46: Tools and Techniques for Managing Project Teams
Observation and conversation
Project performance appraisals
Interpersonal skills
Conflict management

## Slide 47: Conflict Handling Modes
Confrontation: Directly face a conflict using a problem-solving approach
Compromise: Use a give-and-take approach
Smoothing: De-emphasize areas of difference and emphasize areas of agreement
Forcing: The win-lose approach
Withdrawal: Retreat or withdraw from an actual or potential disagreement
Collaborating: Decision makers incorporate different viewpoints and insights to develop consensus and commitment

## Slide 48: Figure 9-11. Conflict Handling Modes

## Slide 49: Conflict Can Be Good
Conflict often produces important results, such as new ideas, better alternatives, and motivation to work harder and more collaboratively
Groupthink: Conformance to the values or ethical standards of a group. Groupthink can develop if there are no conflicting viewpoints
Research suggests that task-related conflict often improves team performance, but emotional conflict often depresses team performance

## Slide 50: Five Dysfunctions of a Team
Patrick Lencioni, author of several books on teams, says that “Teamwork remains the one sustainable competitive advantage that has been large untapped”*
The five dysfunctions of teams are
    Absence of trust
    Fear of conflict
    Lack of commitment
    Avoidance of accountability
    Inattention to results

## Slide 51: Using Software to Assist in Human Resource Management
Software can help in producing RAMS and resource histograms
Project management software includes several features related to human resource management such as
  Assigning resources
  Identifying potential resource shortages or underutilization
  Leveling resources

## Slide 52: Project Resources Involves Much More Than Using Software
Project managers must
  Treat people with consideration and respect
  Understand what motivates them
  Communicate carefully with them
Focus on your goal of enabling project team members to deliver their best work

## Slide 53: Chapter Summary
Project human resource management includes the processes required to make the most effective use of the people involved with a project
Main processes include
  Plan human resource management
  Acquire project team
  Develop project team
  Manage project team

## Slide 54: Questions & answers