## Sheet1
Task/Management | Human Resources | Procurement | Communication | Risk
1. Initiating
1.1 Develop Project Charter | P
1.2 Collect Purchase Requests |  | P
1.3 Identify Stakeholders |  |  | P
1.4 Sponsor/Supplier Search |  |  | P
1.5 Analyse Potential Risks |  |  |  | P
2. Planning
2.1 Plan Human Resource Management | P
2.2 Organize List of Required Assets |  | P
2.3 Plan Communications Management
2.4 Contacting Sponsors |  |  | P
2.5 Plan Risk Management |  |  |  | P
2.6 Identify Risks |  |  |  | P
2.7 Perform Risk Analysis |  |  |  | P
2.8 Plan Risk Responses |  |  |  | P
3. Executing
3.1 Acquire Project Team | P
3.2 Develop Project Team | P
3.3 Manage Project Team | P
3.4 Contacting & Negotiate with Sponsors/Suppliers |  | P
3.5 Conduct Procurement |  | P
3.6 Manage Communications |  |  | P
3.7 Manage Stakeholder Expectations |  |  | P
3.8 Execute Risk Responses |  |  |  | P
4. Monitoring & Controlling
4.1 Monitor Project Team Progress | P
4.2 Control Procurement |  | P
4.3 Control Communications |  |  | P
4.4 Monitor and Control Risks |  |  |  | P
5. Closing
5.1 Close Project | P
5.2 Close Procurements |  | P
5.4 Document Procurement Report |  | P
5.6 Document Report on Losses |  |  |  | P

## Sheet2
Task/Management | Cost
1. Initiating | 1000
1.1 Develop Project Charter | 200
1.2 Collect Purchase Requests | 200
1.3 Identify Stakeholders | 200
1.4 Sponsor/Supplier Search | 200
1.5 Analyse Potential Risks | 200
2. Planning | 1600
2.1 Plan Human Resource Management | 200
2.2 Organize List of Required Assets | 200
2.3 Plan Communications Management | 200
2.4 Contacting Sponsors | 200
2.5 Plan Risk Management | 200
2.6 Identify Risks | 200
2.7 Perform Risk Analysis | 200
2.8 Plan Risk Responses | 200
3. Executing | 1600
3.1 Acquire Project Team | 200
3.2 Develop Project Team | 200
3.3 Manage Project Team | 200
3.4 Contacting & Negotiate with Sponsors/Suppliers | 200
3.5 Conduct Procurement | 200
3.6 Manage Communications | 200
3.7 Manage Stakeholder Expectations | 200
3.8 Execute Risk Responses | 200
4. Monitoring & Controlling | 800
4.1 Monitor Project Team Progress | 200
4.2 Control Procurement | 200
4.3 Control Communications | 200
4.5 Monitor and Control Risks | 200
5. Closing | 1200
5.1 Close Project | 200
5.2 Close Procurements | 200
5.3 Document report on departments' progress | 200
5.4 Document report on obtained supplies/services | 200
5.5 Document report on messeges/mails | 200
5.6 Document report on losses | 200
TOTAL: | 6200

## Sheet5
ResourceName | Amount | Std. Rate | Working Month/Week/Day/Hour | Calculation | Cost
Project Manager | 1 | $4000/mon | 6 Months | $4000 x 6 | 24000
Project Manager Advisor | 1 | $2000/mon | 6 Months | $2000 x 6 | 12000
Software Engineer | 6 | $3000/mon | 6 Months | $3000 x 6 | 18000
UI Designer | 1 | $2500/mon | 6 Months | $2500 x 6 | 15000
Software Tester | 1 | $500/day | 24 Days | $500 x 24 | 12000
Quality Control Manager | 1 | $500/day | 24 Days | $500 x 24 | 12000
Technical Assistant | 2 | $2000/mon | 6 Months | $2000 x 6 | 12000
Negotiator | 1 | $2500/mon | 6 Months | $2500 x 6 | 15000
Procurement Officer | 1 | $2500/mon | 6 Months | $2500 x 6 | 15000
|  |  |  | TOTAL: | 13500