## Sheet1
Task/Management | Human Resources | Procurement | Communication | Risk
1. Initiating
1.1 Develop Project Charter | P
1.2 Collect Purchase Requests |  | P
1.3 Identify Stakeholders |  |  | P
1.4 Sponsor/Supplier Search |  |  | P
1.5 Analyse Potential Risks |  |  |  | P
2. Planning
2.1 Plan Human Resource Management | P
2.2 Organize List of Required Assets |  | P
2.3 Plan Communications Management
2.4 Contacting Sponsors |  |  | P
2.5 Plan Risk Management |  |  |  | P
2.6 Identify Risks |  |  |  | P
2.7 Perform Risk Analysis |  |  |  | P
2.8 Plan Risk Responses |  |  |  | P
3. Executing
3.1 Acquire Project Team | P
3.2 Develop Project Team | P
3.3 Manage Project Team | P
3.4 Contacting & Negotiate with Sponsors/Suppliers |  | P
3.5 Conduct Procurement |  | P
3.6 Manage Communications |  |  | P
3.7 Manage Stakeholder Expectations |  |  | P
3.8 Execute Risk Responses |  |  |  | P
4. Monitoring & Controlling
4.1 Monitor Project Team Progress | P
4.2 Control Procurement |  | P
4.3 Control Communications |  |  | P
4.4 Monitor and Control Risks |  |  |  | P
5. Closing
5.1 Close Project | P
5.2 Close Procurements |  | P
5.4 Document Procurement Report |  | P
5.6 Document Report on Losses |  |  |  | P

## Sheet2
Resource Name | Amount | Std. Rate | Working Month/Week/Day/Hour | Calculation | Cost
Project Manager | 1 | $3000/mon | 4 Months | 7000 x 4 | 28000
Software Engineer | 3 | $2200/mon | 4 Months | 2200 x 4 x 3 | 26400
UI Designer | 1 | $1800/mon | 4 Months | 1800 x 4 | 7200
Software Tester | 1 | $1000/mon | 1 Month | 1000 | 1000
Quality Control | 1 | $1700/day | 4 Months | 1700 x 4 | 6800
IT Security | 1 | $1800/mon | 4 Months | 1800 x 4 | 7200
Technical Assistant | 1 | $1800/mon | 4 Months | 1800 x 4 | 7200
|  |  |  | Total: | 83800

## Sheet3
Task/Management | Budget Cost
1. Initiating | 3500
1.1 Develop Project Charter | 1000
1.2 Collect Purchase Requests | 0
1.3 Identify Stakeholders | 500
1.4 Sponsor/Supplier Search | 500
1.5 Analyse Potential Risks | 1500
2. Planning | 15000
2.1 Plan Human Resource Management | 3000
2.2 Organize List of Required Assets | 1000
2.3 Plan Communications Management | 4000
2.4 Contacting Sponsors | 2000
2.5 Plan Risk Management | 2000
2.6 Identify Risks | 1000
2.7 Perform Risk Analysis | 2000
2.8 Plan Risk Responses | 0
3. Executing | 81000
3.1 Acquire Project Team | 40000
3.2 Develop Project Team | 30000
3.3 Manage Project Team | 0
3.4 Contacting & Negotiate with Sponsors/Suppliers | 1000
3.5 Conduct Procurement | 5000
3.6 Manage Communications | 0
3.7 Manage Stakeholder Expectations | 0
3.8 Execute Risk Responses | 5000
4. Monitoring & Controlling | 7000
4.1 Monitor Project Team Progress | 0
4.2 Control Procurement | 5000
4.3 Control Communications | 2000
4.4 Monitor and Control Risks | 0
5. Closing | 3000
5.1 Close Project | 0
5.2 Close Procurements | 1000
5.4 Document Procurement Report | 1000
5.6 Document Report on Losses | 1000
TOTAL | 109500