## Sheet1
Task/Management | Human Resources | Procurement | Communication | Risk
1. Initiating
1.1 Develop Project Charter | P
1.2 Collect Purchase Requests |  | P
1.3 Identify Stakeholders |  |  | P
1.4 Sponsor/Supplier Search |  |  | P
1.5 Analyse Potential Risks |  |  |  | P
2. Planning
2.1 Plan Human Resource Management | P
2.2 Organize List of Required Assets |  | P
2.3 Plan Communications Management
2.4 Contacting Sponsors |  |  | P
2.5 Plan Risk Management |  |  |  | P
2.6 Identify Risks |  |  |  | P
2.7 Perform Risk Analysis |  |  |  | P
2.8 Plan Risk Responses |  |  |  | P
3. Executing
3.1 Acquire Project Team | P
3.2 Develop Project Team | P
3.3 Manage Project Team | P
3.4 Contacting & Negotiate with Sponsors/Suppliers |  | P
3.5 Conduct Procurement |  | P
3.6 Manage Communications |  |  | P
3.7 Manage Stakeholder Expectations |  |  | P
3.8 Execute Risk Responses |  |  |  | P
4. Monitoring & Controlling
4.1 Monitor Project Team Progress | P
4.2 Control Procurement |  | P
4.3 Control Communications |  |  | P
4.4 Monitor and Control Risks |  |  |  | P
5. Closing
5.1 Close Project | P
5.2 Close Procurements |  | P
5.4 Document Procurement Report |  | P
5.6 Document Report on Losses |  |  |  | P

## Sheet2
Resource Name | Amount | Std. Rate | Working Month/Week/Day/Hour | Calculation | Cost
Project Manager | 1 | $3000/mon | 4 Months | 7000 x 4 | 28000
Software Engineer | 3 | $2200/mon | 4 Months | 2200 x 4 x 3 | 26400
UI Designer | 1 | $1800/mon | 4 Months | 1800 x 4 | 7200
Software Tester | 1 | $1000/mon | 1 Month | 1000 | 1000
Quality Control | 1 | $1700/mon | 4 Months | 1700 x 4 | 6800
IT Security | 1 | $1800/mon | 4 Months | 1800 x 4 | 7200
Technical Assistant | 1 | $1800/mon | 4 Months | 1800 x 4 | 7200
|  |  |  | Total: | 83800

## Sheet3
Task/Management | Budget Cost
1. Initiating | 3500
1.1 Develop Project Charter | 1000
1.2 Collect Purchase Requests | 0
1.3 Identify Stakeholders | 500
1.4 Sponsor/Supplier Search | 500
1.5 Analyse Potential Risks | 1500
2. Planning | 15000
2.1 Plan Human Resource Management | 3000
2.2 Organize List of Required Assets | 1000
2.3 Plan Communications Management | 4000
2.4 Contacting Sponsors | 2000
2.5 Plan Risk Management | 2000
2.6 Identify Risks | 1000
2.7 Perform Risk Analysis | 2000
2.8 Plan Risk Responses | 0
3. Executing | 81000
3.1 Acquire Project Team | 40000
3.2 Develop Project Team | 30000
3.3 Manage Project Team | 0
3.4 Contacting & Negotiate with Sponsors/Suppliers | 1000
3.5 Conduct Procurement | 5000
3.6 Manage Communications | 0
3.7 Manage Stakeholder Expectations | 0
3.8 Execute Risk Responses | 5000
4. Monitoring & Controlling | 7000
4.1 Monitor Project Team Progress | 0
4.2 Control Procurement | 5000
4.3 Control Communications | 2000
4.4 Monitor and Control Risks | 0
5. Closing | 3000
5.1 Close Project | 0
5.2 Close Procurements | 1000
5.4 Document Procurement Report | 1000
5.6 Document Report on Losses | 1000
TOTAL | 109500
Integrated Supply Chain Management Project (ISCMP) | Budget Cost
1 Initiating
1.1 Identify Stakeholders
1.2 System Proposal
1.3 Feasibility Studies
1.3.1 Technical Feasibility Study
1.3.2 Schedule Feasibility Study
1.3.3 Financial Feasibility Study
1.3.4 Resource Feasibility Study
1.4 Develop Project Charter
1.4.1 Determine Project Aim & Objectives
1.4.2 Determine Project Scope
1.4.3 Determine Project Budget
1.4.4 Determine Project Roles
1.4.5 Determine Project Risks
1.4.6 Determine Project Milestones
2 Planning
2.1 Develop Project Plan
2.1.1 Identify Phases & Activities
2.1.2 Create Project Planning Schedule
2.2 Develop Resource Plan
2.2.1 Identify Types of Tasks
2.2.2 Identify Number of Staff
2.2.3 Identify Needed Equipment
2.2.4 Identify Equipment Types & Quantity
2.3 Develop Financial Plan
2.3.1 Identify Labour Costs
2.3.2 Identify Equipment Costs
2.3.3 Identify Miscellaneous Costs
2.4 Develop Quality Plan
2.4.1 Identify Customers Requirements
2.4.2 List Project Deliverables
2.4.3 Define Quality Standards for Deliverables
2.4.4 Customer Approval for Set Targets
2.5 Develop Risk Plan
2.5.1 Identify Project Risks
2.5.2 Categorize & Prioritize Risks
2.6 Develop Communication Plan
2.6.1 List Communications Stakeholders
2.6.2 Define Communication Needs
2.7 Develop Procurement Plan
2.7.1 Determine Procurement Requirements
2.7.2 Identify Needed Procurement
2.7.3 Create Financial Justification
3 Execution
3.1 Requirement Gathering
3.1.1 Client Interview
3.1.2 Construct Use Case
3.1.3 Prototyping
3.2 Procurement
3.2.1 Compare Supplier Prices
3.2.2 Negotiate Prices
3.2.3 Obtain Hardware
3.2.4 Obtain Software
3.3 Staff Management
3.3.1 Recruits Interview
3.3.2 Allocate Human Resources
3.3.3 Labour Tracking
3.3.4 Training Tracking
3.3.5 Time Tracking
3.4 Development
3.4.1 Functional Development
3.4.2 Technical Development
3.4.3 Application Development
3.5 Testing
3.5.1 Application Development Centre Testing
3.5.2 IT Regression Testing
3.4.3 User Acceptance Testing
3.6 System Setup
3.6.1 Hardware Installation
3.6.2 System Installation
4 Monitoring & Controlling
4.1 HR Management
4.1.1 Control Man Days
4.1.2 Monitor Staff Progress
4.2 Procurement Management
4.2.1 Quantity Control
4.2.2 Quality Control
4.3 Quality Deliverables
4.3.1 Testing Reports
5 Closing
5.1 Documentation
5.1.1 Procurement Report
5.1.2 Financial Report
5.1.3 Project Documentation
5.1.4 Stakeholders Approval & Signature
5.2 Formal Acceptance & Information
5.2.1 Inform Stakeholders
5.2.2 Stakeholders Approval & Signature
5.2.3 End Staff Employment
5.2.4 End Supplier Contract