## Slide 1: PRMGT PRESENTATION
RAM
ZAT
YIN
ANG
Project Management
UC3F1805CGD
Build:

## Slide 2
Case Study
Good Life Ptd. Ltd. (GL)
Role:
Project Management
Integrated Supply Chain Management Project (ISCMP)
4 months left
18 issues atm
Us
(right now)
  Create

## Slide 3
Project Methodology
Waterfall Model
  All Processes are pre-defined
  WHY?
  Easy for similar projects
  Assign roles in shorter time
  Low risk

## Slide 4
Project Methodology (cont.)
  HOW?
  SpiraTeam

## Slide 5
Project Management Process
Initiating
Planning
Executing
Monitoring & Controlling
Closing
Knowledge Area(s)
Integration
Scope
Time
Cost
Quality
Human Resource
Communication
Risk
Procurement
(Areas Covered in this presentation)

## Slide 6
Expected ‘Finish Date’ & ‘Budget Cost’
ESTIMATED BUDGET | $280,000.00
Hardware | $50,000.00
Development Software | $80,000.00
Manpower | $100,000.00
RESERVE | $50,000.00
Estimated Cost | $230,000.00
MILESTONES | DATE
Start Project | 11/6/2018
Receive Project Approval | 19/6/2018
Complete Planning Phase | 13/7/2018
Complete ISCMP Requirements | 24/7/2018
Complete ISCMP Development | 20/9/2018
Complete Testing | 9/10/2018
ISCMP Installation | 15/10/2018
Functional ICSMP | 22/10/2018
Project End | 30/10/2018

## Slide 7
Work Breakdown Structure (WBS)
Planning
Initiating

## Slide 8
Work Breakdown Structure (WBS)
Execution
Monitoring & Controlling
Closing

## Slide 9
Scope Statement
Acceptance Criteria
  Contains features in typical Supply Chain Management (SCM) Software
  Inventory + Transportation + Yard + Labor + Warehouse managements
Deliverables
  SCM software with centralized data warehouse that calculates faster.

## Slide 10
Assumptions
  Advisors required for project team
  Improvised hardware needed
  Time management needed
Constraints
  Time frames
  Resources (hardware)
  Activity performance
Scope Statement (cont.)
Exclusions
  Lack of security services
  Capped logs duration
  Limited access to current system(s)
  Limited language available

## Slide 11
Table of Issues (1)
Integration Management |  |  | 
Issue No. | Issues | Project Management Process | Tools & Technique
4 | The PC and server hardware technical specifications were constantly being changed to suit new or added requirements. | Planning | Expert Judgement: Get the latest and most powerful hardware technical specifications so the requirement to go for higher specifications would be very small change.
5 | Requirements keep coming in from users almost daily where the GITS-ADC Team Lead keeps on accepting them without hesitation. | Execution | Negotiations: Keep the requirements update monthly and inform the Team Lead to not take requirements when the team is already full of work.
15 | Technical skills were especially lacking in the network and security areas. | Planning | Group Decision-Making Techniques: Hiring a professional technical team to ensure all technical problems to assist with.

## Slide 12
Table of Issues (2)
Human Resource Management |  |  | 
Issue No. | Issues | Project Management Process | Tools & Technique
6 | There was redundancy of work performed as the Work Breakdown Structure (WBS) was done separately by each respective department and the Project Manager did not review and then consolidate those WBSs into one wholistic WBS | Initiation | Pre-Assignment: Assigning teammates to work on tasks following the WBS and provide regular updates to the project manager.
7 | Most of the team members have been focusing more on their daily operation support rather than tasks being assigned by the Project Manager or their respective Team Lead | Execution | Performance Reviews: Conduct a daily check routine to ensure the project plan is being followed and ensure the team members are doing their task as provided.
13 | There was no clear project organizational structure to manage the project. | Planning | Organization Chart: With organization chart, clear organizational structure is developed start from the highest management till the individual responsibility.

## Slide 13
Communication Management |  |  | 
Issue No. | Issues | Project Management Process | Tools & Technique
1 | The steering committee (which consist of the board of directors, CEO and Senior Managers of the organization) do not recall of being presented the project feasibility study by the Project Sponsor or the Project Manager to them. | Initiation | Communication Requirement Analysis: Determine all stakeholders means of communications, calling intervals and recommended timing plus the duration
6 | There was redundancy of work performed as the Work Breakdown Structure (WBS) was done separately by each respective department and the Project Manager did not review and then consolidate those WBSs into one wholistic WBS | Initiation; Planning | Meetings: Gathers the stakeholders for a face to face deliver more on the working requirements for a complete and centralized WBS. Issue Logs: Identify all issues that the project has and delegate manpower easier based on the problem-solving strategies’ comparison
7 | Most of the team members have been focusing more on their daily operation support rather than tasks being assigned by the Project Manager or their respective Team Lead | Execution | Performance Reporting: Conduct a daily-to-monthly check routine to ensure the project plan is being followed and ensure the team members are doing their task as provided.
Table of Issues (3)

## Slide 14
Risk Management |  |  | 
Issue No. | Issues | Project Management Process | Tools & Technique
11 | The testing plan was not developed yet | Planning | Benchmarking: Pre-plan for 2 types of testing such as white-box testing and black-box testing. Also have phases on test on such as alpha phase, beta phase and so on.
12 | There was not even a clear designated sponsor (or sponsors) for the project. | Planning | Communication Technology: Ensure the stakeholders for the project before the project starts.
15 | Technical skills were especially lacking in the network and security areas. | Planning | Group Decision-Making Techniques: Hiring a professional technical team to ensure all technical problems to assist with.
Table of Issues (4)

## Slide 15
Procurement Management |  |  | 
Issue No. | Issues | Project Management Process | Tools & Technique
9 | IT assets acquisition and spending were through PROC Manager with suppliers without going through a proper tendering process. | Execution | Inspections and Audits: Having inspections and audits to confirm supplies from suppliers.
10 | Purchasing of IT assets without a proper tendering process has led to overrun by budget. | Planning | Expert Judgement: Get the latest and most powerful hardware technical specifications so the requirement to go for higher specifications would be very small change.
18 | The hardware and software delivery were still being negotiated with some potential vendors while there were only four (4) months to complete the project. | Planning | Performance Reporting: Performance updates need to be provided to the project manager, the project manager will be able to handle the issues and updates needed to be provided to the stakeholders and the suppliers for the supplies.
Table of Issues (5)

## Slide 16
Quality Management |  |  | 
Issue No. | Issues | Project Management Process | Tools & Technique
9 | IT assets acquisition and spending were through PROC Manager with suppliers without going through a proper tendering process. | Execution | Process Analysis: Conduct testing and checking the status to ensure the quality is top-notch.
15 | Technical skills were especially lacking in the network and security areas. | Planning | Group Decision-Making Techniques: Hiring a professional technical team to ensure all technical problems to assist with.
18 | The hardware and software delivery were still being negotiated with some potential vendors while there were only four (4) months to complete the project. | Planning | Design of Experiment: Testing is expected in the process, thus planning out the hardware and software that would be of use.
Table of Issues (6)

## Slide 17
Scope Management |  |  | 
Issue No. | Issues | Project Management Process | Tools & Technique
2 | The project approval was not formally documented. | Initiation | Alternatives Identifications: Use multiple ways to confirm all approval and document them in hard copy as well as soft copy.
3 | There is no evidence that a proper project management process was followed. | Initiation | Inspection: Check all department and confirm all with evidence. Double confirm them if necessary.
14 | The Project Manager’s authority was constantly overridden by the department head managers. | Controlling & Monitoring | Variance Analysis: Keep all the department head managers under control, as well as keep them under monitor if there were anything wrong to happen.
Table of Issues (7)

## Slide 18
Gantt Chart (simplified ver.)

## Slide 19
Network Diagram (also simplified ver.)

## Slide 20
Quality Management Plan(1)
Planning
  Design of Experiments
    ‘comparing hardware and software performance relative to pricing in ISCMP’
Issue 18: Hardware & Software Delivery still in Negotiations

## Slide 21
Quality Management Plan(2)
Assurance
  Process Analysis
    7 steps of Tendering
Issue 9: IT assets spending lack proper Tendering Process
Determine Tendering Types
Prepare Request for Tendering
Inviting Tenders
Response from Suppliers
Evaluation & Selection
Notification & Debriefing
Establish & Manage Contracts

## Slide 22
Quality Management Plan(3)
Control
  Group Decision-Making Techniques
    Brainstorming
    + Expert Judgement (guide & evaluation)
    TOPIC: Requirements of ISCMP Network & Security parts
Issue 15: Lacking Network & Security-based skills

## Slide 23
Cutover Strategy & Transition Plan
Parallel Operation
  New system added
  while old system still running
  WHY?
  ISCMP == Critical Application
  Totally different core database compared to old system
  HOW?
  Old system: Placeholder Backup
  New System: Practical Training + User Acceptance Test

## Slide 24
Lesson Learned Report
(Individual Parts)

## Slide 25
Human Resource Management
?

## Slide 26
Procurement Management
?

## Slide 27
Communication Management(1)
PLAN
  Communication Requirements Analysis
    Understand everyone’s contacts
    Prevent ‘hit-and-miss’ scenarios
Issue 1: Steering Committee didn’t recall of feasibility study presentation
STAKEHOLDER NAME | ROLE(S) | DOCUMENT (NAME & FORMAT) | AVAILABLE IN (PLATFORM) | CONTACT BY (DEADLINE)
Monos Krome | Quality Control | Progress Report (Printed Copy) | Face-to-Face; WeChat | Each week, Thursday
Lunaire Mun | UI (User Interface) Designer | User Interface Design Draft (.ai Format & Printed Copy) | E-mail; Face-to-Face | 24/7/2018
Apolloa Sun | Software Engineer | Status Report (E-mail) | Discord; E-mail; LINE | Each week, Monday
e.g.

## Slide 28
Communication Management(2)
MANAGE
  Performance Reporting
    1 representative from each section
    Daily/Weekly/Monthly intervals
    Status Report + Progress Report + Forecast
Issue 7: Wrong priority levels among team members

## Slide 29
Communication Management(3)
Issue 6: WBS are all separated & not complete
CONTROL
  Issue Logs + Meeting
    Issue Log: provide meeting guidelines
    Meeting: deliver tasks & report issue log progress

## Slide 30
Risk Management
Issue 11: The testing plan was not developed yet
PLAN
  Benchmarking
    Pre-plan white-box testing and black-box testing
    Have multiple testing phases such as alpha phase, beta phase and so on.

## Slide 31
Risk Management(2)
Issue 12: There was no clear designated sponsor(s) for the project
MANAGE
  Communication Technology
    Ensure the stakeholders for the project before the project starts
    Prepare better proposal or look for other sponsors

## Slide 32
Risk Management(3)
Issue 15: Technical skills were especially lacking in the network and security areas
CONTROL
  Group Decision-Making Techniques
    Hiring a professional technical team to assist on the problem.
    Outsource modules to vendors

## Slide 33
Conclusion
Don’t fuck up your own project so other people have to deal with all the incoming shits.
The end.

## Slide 34
Q & A
*
* Hah, we won’t question you. We’ll only doubt you.